## Dashboard
Feral Pig / Pest-Control Patent & Business Buildout
Project control baseline - 2026-09-03
Metric | Value | Definition / gate | Current Gate | State | Reason | Required next evidence
Set 1 claims drafted | 2 | Rows in Claim Inventory with status = drafted/under review/attorney-reviewed/final | Provisional filing | NOT READY | Known enablement/written-description gaps remain | Concrete recognition, population-membership, actuation and safety disclosure + attorney review
Set 1 independent claims drafted | 2 | Target = 3 | Set 1 complete | NO | Only Claims 1 and 20 logged as drafted | Mid-scope independent + 17 dependents + dependency/risk review
Set 1 dependent claims drafted | 0 | Target = 17 | Set 2 | LOCKED | Set 1 incomplete; no written distinct-invention justification | Do not begin
Set 1 claim slots reserved | 20 | Target = 20 | External technical disclosure | LOCKED | Public-disclosure/IP risk | NDA or filing first
Blocking risks open | 11 | Any risk register row marked Blocking = Yes and Status != Resolved | Pilot deployment | NOT READY | Regulatory path not mapped | EPA/state/wildlife/operator approvals and safety protocol
Near-term tasks complete | 5 | Tasks due in 1-week horizon with Status = Complete | Prior-art confidence | LOW | Transcript contains direct technical overlap clues; formal search pending | Primary-source tracing + Patent Public Search/Google Patents/professional search
MPEP update authorities indexed | 29 | Official post-2024 authorities catalogued in MPEP Update Register

## Claim Inventory
claim # | set # | independent/dependent | parent claim | scope summary | full claim language | status | risk flags | last-updated date
1 | 1 | independent |  | Broad pest identification + lethal action | A method of killing a pest by: identifying a pest using video recognition technology; and using a lethal means to kill the pest. | drafted | 112(f); 112(b); written-description gap; enablement gap; prior-art risk; restriction risk; regulatory/deployment issue | 2026-09-03
2 | 1
3 | 1
4 | 1
5 | 1
6 | 1
7 | 1
8 | 1
9 | 1
10 | 1
11 | 1
12 | 1
13 | 1
14 | 1
15 | 1
16 | 1
17 | 1
18 | 1
19 | 1
20 | 1 | independent |  | Narrow feral-pig local-population identification + selectively timed/delivered general poison | A method of selectively killing a feral pig by: identifying members of a local feral pig population using audio or video recognition technology, or a combination thereof; identifying when all members of the local feral pig population are present; and selectively administering a general poison to all members of the local feral pig population, wherein the general poison kills the feral pig. | drafted | 112(b); written-description gap; enablement gap; prior-art risk; restriction risk; regulatory/deployment issue | 2026-09-03

## Task Register
ID | Workstream | Task | Deliverable / acceptance criterion | Owner | Status | Priority | Horizon | Dependency | Risk / note | Last updated
PAT-001 | Patent | Create claim inventory tracker | Tracker exists and is single source of truth | Robert/AI | Complete | Critical | 1-week |  | Mandatory before further claim drafting | 2026-09-03
PAT-002 | Patent | Draft enabling provisional specification skeleton | Sections for field/background/summary/definitions/architecture/recognition/population ID/lethal delivery/safety/variants/examples/data flows/hardware-software/deployment/failure cases | Robert/AI | In Progress | Critical | 1-week | PAT-001 | Do not let claim perfection delay an enabling filing | 2026-09-03
PAT-003 | Patent | Elicit missing technical details | Written answers or diagrams sufficient to support recognition models, thresholds, group membership logic, actuation, safety interlocks, failure modes | Robert | Not Started | Critical | 1-week | PAT-002 | Blocking enablement risk | 2026-09-03
PAT-004 | Patent | Draft Set 1 mid-scope independent claim | One independent claim bridging generic pest-control and narrow feral-pig embodiment; logged in tracker | Robert/AI | Not Started | High | 1-week | PAT-003 | Do not draft Set 2 | 2026-09-03
PAT-005 | Patent | Draft 17 dependent claims | Exactly 17 dependent claims with valid dependency tree and tracker entries | Robert/AI | Not Started | High | 1-week | PAT-004 | Set complete only at 3 independent + 17 dependent | 2026-09-03
PAT-006 | Patent | Resolve 'lethal means' 112(f) strategy | Specification deliberately supports MPF treatment or claims recite concrete acts/materials/structures | Robert/Patent counsel | Not Started | Critical | 1-week | PAT-002 | Known 112(f)/112(b) risk | 2026-09-03
PAT-007 | Patent | Tighten Claim 20 selective-delivery semantics | Differentiate nonselective toxicity from selective access/timing/delivery; update tracker | Robert/AI | Not Started | Critical | 1-week | PAT-003 | Known 112(b) risk | 2026-09-03
PAT-008 | Patent | Document 'all members present' implementation | Recognition, individual/group ID, confidence thresholds, sampling windows, exclusion criteria, false positive/negative handling | Robert | Not Started | Critical | 1-week | PAT-003 | Blocking written-description/enablement risk | 2026-09-03
PAT-009 | Prior Art | Trace transcript references to primary sources | Identify LSU feeder work, Kaput/warfarin documents, sounder trapping systems, source video/news/publications | AI/Robert | In Progress | Critical | 1-week |  | Transcript is lead source, not prior-art proof | 2026-09-03
PAT-010 | Prior Art | Run preliminary AI prior-art triage | Search patents/nonpatent literature for audio/video recognition + selective lethal delivery + sounder-completeness logic | AI | Complete | High | 1-week | PAT-009 | Triage only; later USPTO/PPS + Google Patents/pro search | 2026-09-03
PAT-011 | Prior Art | Run formal patent search | USPTO Patent Public Search + Google Patents + CPC/keyword/citation searching; log search strings/results | Robert/Patent searcher | Not Started | Critical | 1-month | PAT-010 | Required before nonprovisional strategy | 2026-09-03
PAT-012 | Patent | Attorney review pass | Licensed patent attorney reviews provisional and claim-support map | Patent counsel | Not Started | Critical | 1-week | PAT-002,PAT-003 | No filing/submission before review | 2026-09-03
PAT-013 | Patent | File provisional when enabling | Specification, drawings, cover sheet, inventor data, fee; filing receipt archived | Robert/Patent counsel | Not Started | Critical | 1-week | PAT-012 | Filing gated by enablement, not claim perfection | 2026-09-03
MPEP-001 | Legal Research | Index current MPEP + post-cutoff updates | Current MPEP revision, consolidated laws/rules, Subsequent Publications, superseding memoranda indexed | AI | Complete | Critical | 1-week |  | Current MPEP only current through 2024-01-31 | 2026-09-03
MPEP-002 | Legal Research | Build MPEP PDF authority pack | Downloadable manifest/index plus official PDF links; local bundle where source hosting permits | AI | Complete | High | 1-week | MPEP-001 | USPTO host currently blocks direct sandbox mirroring; hyperlink pack used as audit trail | 2026-09-03
MPEP-003 | Legal Research | Add post-July-20-2026 practice changes | Include Aug. 3, 2026 DOCX filing process notice; screen later notices for MPEP impact | AI | Complete | High | 1-week | MPEP-001 | Official Subsequent Publications PDF is current only through 2026-07-20 | 2026-09-03
BUS-001 | Business | Define customer/problem segments | Rank agencies, landowners, farms, operators, airports, conservation stakeholders by pain and buying process | Robert/AI | Not Started | High | 1-month |  | Separate patentability from product-market fit | 2026-09-03
BUS-002 | Business | Define product/service architectures | Hardware, SaaS/recognition, feeder/actuator, managed control service, data/licensing variants | Robert/AI | Not Started | High | 1-month | PAT-003 | Avoid premature technical disclosure | 2026-09-03
BUS-003 | Business | Build regulatory map | EPA pesticide/FIFRA; state pesticide/wildlife rules; USDA/APHIS; carcass/environmental controls; firearms/aircraft if applicable | AI/Regulatory counsel | Not Started | Critical | 1-month |  | Deployment legality independent of patentability | 2026-09-03
ORG-001 | Company/IP | Settle inventorship/conception record | Signed invention/conception chronology identifying contribution by claim concept | Robert/Co-inventors/Counsel | Not Started | Critical | 1-month |  | Complete before equity/IP assignment | 2026-09-03
ORG-002 | Company/IP | Form entity and IP-assignment plan | Entity structure and assignment instruments selected | Robert/Corporate counsel | Not Started | High | 1-month | ORG-001 | Budget/tax/legal review required | 2026-09-03
FUND-001 | Funding | Funding opportunity sweep | SBIR/STTR + federal/state + Mid-Atlantic/Midwest opportunities with deadlines/fit | AI | Not Started | High | 1-month |  | Use actual current deadlines | 2026-09-03
FUND-002 | Funding | Select strongest grant cycle | Decision memo with fit, deadline, eligibility, effort, and IP terms | Robert/AI | Not Started | High | 1-month | FUND-001 | Begin application after selection | 2026-09-03
PART-001 | Partnerships | Build experimental-use target list | USDA/APHIS, state agencies, universities, landowners, farms/operators; Mid-Atlantic/Midwest first | AI | Not Started | High | 1-month |  | Pre-filing outreach = target identification only | 2026-09-03
PART-002 | Partnerships | Prepare NDA-first outreach package | Non-confidential teaser + NDA + post-filing technical deck outline | Robert/Counsel | Not Started | Critical | 1-month | PAT-013 | No substantive disclosure pre-filing without NDA | 2026-09-03
GOV-001 | Governance | Check AI data-retention/training settings | Document settings and approved disclosure workflow | Robert | Not Started | Critical | 1-week |  | Public/confidentiality risk | 2026-09-03
GOV-002 | Governance | Establish repository structure | /src /tests /docs /ci plus /docs/attic; Git LFS policy for large binaries | Robert/AI | Not Started | Medium | 1-week |  | Preserve audit trail and versions | 2026-09-03
PAT-014 | Prior Art | Claim-chart three blocking patent references | Element-by-element charts for Claim 1 and Claim 20 against US10368539B2, US20210315186A1, and US20140261201A1; identify missing/distinguishing limitations and combination risk | AI/Robert/Patent counsel | Not Started | Critical | 1-week | PAT-010 | Complete before materially refining the mid-scope independent claim

## Risk Register
Risk ID | Category | Description | Affected artifact/claim | Mitigation / evidence needed | Blocking | Status | Owner | Last updated
R-112F | 112(f) | 'Lethal means' could be construed as a means-plus-function/functional placeholder without adequate corresponding disclosure. | Claim 1 / specification | Choose deliberate MPF support or recite concrete acts/materials/structures; provide embodiments for each lethal modality. | Yes | Open | Robert/Counsel | 2026-09-03
R-112B-20 | 112(b) | Claim 20's 'selectively administering' a 'general poison' to 'all members' can read internally inconsistent. | Claim 20 | Define selectivity as delivery/access/timing or gating, not toxic selectivity; reword consistently. | Yes | Open | Robert/AI | 2026-09-03
R-WD-ALL | written-description gap | 'Identifying when all members are present' lacks disclosed operational criteria. | Claim 20 / specification | Describe population roster, unknown-member handling, identity confidence, dwell/window rules, re-entry, sensor coverage, and abort logic. | Yes | Open | Robert | 2026-09-03
R-EN-RECOG | enablement gap | Recognition pipeline may be stated at result level without data/model/hardware and error handling detail. | All claims | Add sensor modalities, preprocessing, model families, training/inference, thresholds, latency, environmental variation, false-positive controls. | Yes | Open | Robert | 2026-09-03
R-PA-LSU | prior-art risk | Transcript reports LSU testing a feeder that dispenses poisoned bait based on feral-hog voice recognition. | Claims 1/20 and selective-delivery embodiments | Trace primary source, patent families, inventors/assignees, dates, claim scope, and combine with sounder-completeness art. | Yes | Open | AI/Robert | 2026-09-03
R-PA-SOUNDER | prior-art risk | Whole-sounder capture/management is known in trapping practice and may supply motivation for group-completeness logic. | Claim 20 | Search trap-control patents/literature for remote gates, camera counting, sounder recognition, wait-for-all rules. | Yes | Open | AI/Robert | 2026-09-03
R-RESTRICT | restriction risk | Broad pest genus and narrow feral-pig species embodiments may be treated as distinct inventions/species. | Set 1 | Draft shared technical core and dependency ladder; maintain restriction hedge but do not assume examiner grouping. | No | Open | Counsel | 2026-09-03
R-REG | regulatory/deployment issue | Poison/pesticide/wildlife-control deployment may require federal/state approvals and could constrain embodiments/business model. | Product / pilots | Separate patent scope from deployment claims; build regulatory map; do not imply lawful field use without approvals. | No | Open | Regulatory counsel | 2026-09-03
R-INVENT | inventorship/ownership issue | Conception contributions and ownership not yet fixed in writing. | All IP / company | Prepare conception chronology and counsel-reviewed assignment plan before equity/assignment decisions. | Yes | Open | Robert/Counsel | 2026-09-03
R-DISC | disclosure risk | External discussion before filing may create loss-of-rights/foreign-filing risks. | All IP | NDA first; non-confidential teaser before filing; log disclosures. | Yes | Open | Robert | 2026-09-03
R-PA-VIDEO-KILL | prior-art risk | US10368539B2: camera/image recognition identifies a target species and energizes electrodes to euthanize the matching animal; materially overlaps generic video-recognition + lethal-means scope. | Claim 1; mid-scope independent | Prepare element-by-element claim chart; identify technical distinctions before further broad-claim refinement. | Yes | Open | Robert / patent counsel | 2026-09-03
R-PA-USDA-AV | prior-art risk | US20210315186A1 (USDA): audio/visual target-species recognition autonomously enables wildlife-management devices, including toxicant delivery; feral swine are expressly contemplated. | Claim 1; mid-scope independent; Claim 20 | Claim-chart claims 1, 7-13, 17-18 and feral-swine embodiments; search family/citations in USPTO Patent Public Search. | Yes | Open | Robert / patent counsel | 2026-09-03
R-PA-BOAR-FEEDER | prior-art risk | US20140261201A1: species-selective wild-boar feeding systems contemplate poison for population control/local-population elimination, creating risk around selective delivery of generally toxic bait. | Claim 20 and dependent-claim space | Claim-chart feeder gating, species selectivity, poison administration, and population-control disclosures; search continuations/citations. | Yes | Open | Robert / patent counsel | 2026-09-03

## Source Inventory
Source ID | Type | Title / description | Date | Primary/secondary | Key relevance | Action | Status | Source / path
SRC-001 | Project file | John Oliver Special Report on Feral Pigs - transcript | 2026-06-28 | Secondary / lead source | Problem scale; sounder trapping; poison risks; LSU voice-recognition poisoned-bait feeder; contraceptive/hunting/trapping approaches | Trace each technical assertion to primary source and prior art | Ingested | /mnt/data/2026-06-28 John Oliver Special Report on Feral Pigs – Transcript.docx
SRC-002 | USPTO | MPEP Ninth Edition, Revision 01.2024 | 2024-11 | Primary agency manual | Baseline examination procedure; current only through 2024-01-31 | Use with subsequent publications + current laws/rules | Indexed | https://www.uspto.gov/web/offices/pac/mpep/
SRC-003 | USPTO | Subsequent Publications (After January 31, 2024) - July 2026 Update | 2026-07 | Primary agency update index | Official list of post-cutoff changes under consideration for future MPEP; identifies superseding materials | Use as authority manifest | Indexed | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
SRC-PA-001 | Patent publication | US10368539B2 - Species specific extermination device | 2013-05-09 priority; 2019-08-06 grant | Primary patent document | Camera/image recognition used to gate lethal electrical actuation; major Claim 1 patentability risk. | Claim-chart claims and family; verify prosecution/citations in USPTO Patent Public Search. | Reviewed - triage | https://patents.google.com/patent/US10368539B2/en
SRC-PA-002 | Patent publication | US20210315186A1 - Intelligent dual sensory species-specific recognition trigger system | 2020-04-14 priority; 2021-10-14 publication | Primary patent document | USDA audio+visual species recognition; autonomous wildlife-device activation; toxicants; feral swine. | Claim-chart claims 1, 7-13, 17-18 and embodiments; verify family/citations in USPTO Patent Public Search. | Reviewed - triage | https://patents.google.com/patent/US20210315186A1/en
SRC-PA-003 | Patent publication | US20140261201A1 / US9295225B2 - Species specific feeder | 2013-03-15 priority; 2014-09-18 publication | Primary patent document | Species-selective wild-boar feeder; poison/population-control composition; local-population elimination. | Claim-chart species gating, poison delivery, and local-population language; search continuations/citations. | Reviewed - triage | https://patents.google.com/patent/US20140261201A1/en
SRC-007 | USPTO | MPEP 211 / provisional priority support | current MPEP | Primary agency manual | Later claim receives provisional benefit only if provisional adequately supports and enables subject matter | Use as drafting gate | Indexed | https://www.uspto.gov/web/offices/pac/mpep/s211.html

## MPEP Update Register
Date | Category | Authority / title | Citation / type | Effective / applicable | Status relative to MPEP | Project relevance | Official source
2024-02-27 | Patent notice/guidance | Updated Guidance for Making a Proper Determination of Obviousness | 89 FR 14449 + examiner memorandum | 2024-02-27 | Post-cutoff; future-MPEP candidate | High - 103 obviousness analysis | https://www.uspto.gov/patents/laws/examination-policy/memoranda-examining-corps
2024-03-18 | Patent notice/guidance | Resources for Examining Means-Plus-Function and Step-Plus-Function Claim Limitations | 89 FR 19817 + examiner memorandum | 2024-03-20 notice | Post-cutoff; future-MPEP candidate | Critical - Claim 1 'lethal means' | https://www.uspto.gov/patents/laws/examination-policy/memoranda-examining-corps
2024-03-22 | Patent rule | Signature Requirements Related to Acceptance of Electronic Signatures for Patent Correspondence | 89 FR 20321 + memorandum/examples | 2024-03-22 | Post-cutoff rule | Low/filing administration | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2024-03-29 | Patent rule | Electronic Submission of Federal Circuit Appeal/Judicial Review Notices | 89 FR 22084 | 2024-03-29 | Post-cutoff rule | Low | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2024-05-03 | Patent rule | Adoption of Updated WIPO Standard ST.26; Revision to Incorporation by Reference | 89 FR 36677 | 2024-07-01 | Post-cutoff rule | Low unless sequence listings | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2024-06-12 | PTAB rule | Pre-Issuance Internal Circulation and Review of PTAB Decisions | 89 FR 49808 | 2024-07-12 | Post-cutoff rule | Low | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2024-09-18 | PTAB rule | Motion To Amend Practice in AIA Trial Proceedings | 89 FR 76421 | 2024-10-18 | Post-cutoff rule | Low | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2024-10-01 | PTAB rule | Director Review of PTAB Decisions | 89 FR 79744 | 2024-10-31 | Post-cutoff rule | Low | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2024-10-10 | PTAB rule | Expanding Opportunities To Appear Before PTAB | 89 FR 82172 | 2024-11-12 | Post-cutoff rule | Low | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2024-11-20 | Patent rule | Setting and Adjusting Patent Fees During FY2025 | 89 FR 91898; correction 90 FR 3036 | 2025-01-19 | Post-cutoff rule | Medium - filing/prosecution budget | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2024-04-11 | Practice guidance | Guidance on Use of Artificial Intelligence-Based Tools in Practice Before USPTO | 89 FR 25609 | 2024-04-11 | Post-cutoff guidance | High - AI-assisted drafting/use | https://www.uspto.gov/initiatives/artificial-intelligence/artificial-intelligence-resources
2024-07-17 | Eligibility guidance | 2024 Guidance Update on Patent Subject Matter Eligibility, Including on Artificial Intelligence | 89 FR 58128 + 2024 AI SME examples + memorandum | 2024-07-17 | Post-cutoff guidance | High - recognition/AI claims | https://www.uspto.gov/patents/laws/examination-policy/subject-matter-eligibility
2025-01-14 | MPEP superseding memo | Revised Form Paragraphs for Design Patents and Applications | TC 2900 memorandum | 2025-01-14 | Explicitly supersedes portions of current MPEP | Low | https://www.uspto.gov/web/offices/pac/mpep/
2025-01-17 | MPEP superseding memo | Revised/New Form Paragraphs re FY2025 Patent Fees | examiner memorandum | 2025-01-17 | Explicitly supersedes portions of current MPEP | Medium | https://www.uspto.gov/web/offices/pac/mpep/
2025-06-10 | Patent rule | Discontinuation of Accelerated Examination Program for Utility Applications | 90 FR 24324 | 2025-07-10 | Post-cutoff rule | Medium - prosecution planning | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2025-07-08 | Patent rule | 2025 Increase of Annual Limit on Accepted Requests for Prioritized Examination | 90 FR 29990 | 2025-07-08 | Post-cutoff rule | Medium - Track One planning | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2025-08-04 | Eligibility guidance | Reminders on evaluating subject matter eligibility under 35 USC 101 | examiner memorandum | 2025-08-04 | Post-cutoff guidance | High - AI/recognition claims | https://www.uspto.gov/patents/laws/examination-policy/subject-matter-eligibility
2025-09-11 | Electronic filing guidance | Updated Legal Framework for Patent Electronic System | 90 FR 44050 | 2025-09-11 | Post-cutoff guidance | Medium - filing workflow | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2025-10-24 | MPEP superseding memo | PE2E Similarity Search guidance | examiner memorandum | 2025-10-24 | Explicitly supersedes portions of current MPEP | Medium - examination search practices | https://www.uspto.gov/web/offices/pac/mpep/
2025-10-24 | MPEP superseding memo | False assertions/certifications of entity status | examiner memorandum | 2025-10-24 | Explicitly supersedes portions of current MPEP | Medium - fee/entity compliance | https://www.uspto.gov/web/offices/pac/mpep/
2025-11-28 | Inventorship guidance | Revised Inventorship Guidance for AI-Assisted Inventions | 90 FR 54636 | 2025-11-28 | Post-cutoff guidance; rescinds Feb. 2024 AI inventorship guidance | High - AI use + conception record | https://www.uspto.gov/subscription-center/2025/revised-inventorship-guidance-ai-assisted-inventions
2025-12-04 | Eligibility guidance | Subject Matter Eligibility Declarations | examiner memorandum | 2025-12-04 | Post-cutoff guidance | Medium | https://www.uspto.gov/patents/laws/examination-policy/subject-matter-eligibility
2025-12-05 | MPEP superseding memo | Advance notice of change to MPEP in light of Ex Parte Desjardins | examiner memorandum | 2025-12-05 | Explicitly supersedes portions of current MPEP | High - technological-improvement arguments | https://www.uspto.gov/web/offices/pac/mpep/ANC-Desjardins-Memo-12-5-25.pdf
2026-03-20 | Patent rule | Required Use by Foreign Applicants and Patent Owners of a Patent Practitioner | 91 FR 13510 | 2026-07-20 | Post-cutoff rule | Low unless foreign applicant/owner | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2026-03-13 | Design eligibility guidance | Supplemental Guidance for Computer-Generated Interfaces and Icons | 91 FR 12394 | 2026-03-13 | Post-cutoff guidance | Low for utility filing | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2026-04-30 | Eligibility guidance | Best Practices for Submission of Rule 132 Subject Matter Eligibility Declarations (SMEDs) | memorandum | 2026-04-30 | Post-cutoff guidance; supersedes Dec. 4 best-practices memo | Medium - future prosecution | https://www.uspto.gov/patents/laws/examination-policy/subject-matter-eligibility
2026-06-24 | Patent rule | Conditions for Additional Information and Fee in Petitions Based on Unintentional Delay | 91 FR 37826 | 2026-08-13 | Post-cutoff rule | Low/administrative | https://www.uspto.gov/web/offices/pac/mpep/subsequent-publications.pdf
2026-07-17 | Examiner memo | Requirement for Foreign Applicants to use Patent Practitioner - implementation | examiner memorandum + examples | 2026-07-20 | Post-cutoff guidance | Low unless foreign applicant/owner | https://www.uspto.gov/patents/laws/examination-policy/memoranda-examining-corps
2026-08-03 | Official Gazette practice notice | Update to Procedure for Filing Patent Applications in DOCX Format through Patent Center | Official Gazette notice (published 2026-09-01) | Aug. 2026 process change | Post-July-20 supplement; MPEP 502.05 pending revision | High - filing workflow / source-format verification | https://www.uspto.gov/patents/laws/patent-related-notices/patent-related-notices-2026

## Business Skeleton
Block | Questions to resolve | Evidence / output | Status | Dependency
Problem | Where is feral-pig damage costly enough to justify automated control? Who bears the loss? | Segmented problem statement + loss estimates + buyer map | Not Started | Source validation
Customer | Who can legally buy/deploy/control the system? | ICP matrix: agency, landowner, farm, operator, airport, conservation manager | Not Started | Regulatory map
Value proposition | What measurable outcome improves: removals/night, labor, non-target risk, crop damage, surveillance burden? | Quantified benefit hypotheses + pilot metrics | Not Started | Pilot design
Product | What is sold: recognition module, feeder/actuator, full station, managed service, licensing? | Architecture and BOM/service variants | Not Started | Technical disclosure
IP moat | Which technical features are claimable and hard to design around? | Claim-support/prior-art matrix | Not Started | Prior-art search
Regulatory | What pesticide/wildlife/device approvals govern each embodiment? | Jurisdiction-by-jurisdiction deployment matrix | Not Started | Counsel/agency research
Go-to-market | Direct agency procurement, dealers/operators, OEM licensing, pilot-to-contract? | Channel and procurement strategy | Not Started | Customer interviews
Revenue | Hardware margin, recurring software/data, consumables, service, licensing | Unit-economics model | Not Started | Product choice
Data moat | Who owns field video/audio/labels and derived models? | Data rights clause set + retention/security policy | Not Started | Partnership/NDA
Pilot | What can be tested safely and legally without compromising IP? | Pilot protocol + kill/no-kill phases + success criteria | Not Started | Patent filing + regulatory