PATENT DRAFTING MASTER CONTROL

Recognition-Gated Population-Control Platform - v0.5 - 2026-09-03

1. Canonical patent state

• Specification v0.4: 280 numbered specification paragraphs, 135 claims, abstract, corrected FIGS. 1-12 reference-numeral integration, and restored Definitions heading; visual QA passed.

• Figures v0.2: twelve patent-style line drawings; FIG. 4 identity-record label and FIG. 9 sensor-label defects corrected; visual QA passed.

• Claims v0.4: 135 working claims across 14 independent claim families; no claim-count ceiling.

• Patent Support and Figure Audit v0.2: figure audit passes and 63 independent-claim limitation rows map exact paragraph/figure support and blocking status.

• Inventor Confirmation Questionnaire v0.1: prepared as a non-leading conception/support instrument; inventor responses are pending.

• Tracker: Figure Numerals, Figure-Spec Audit, Detailed Claim-Spec Audit, Independent Family Audit and current task state are synchronized.

2. Blocking support branches

• Claim 11/local population: written support is extensive, but inventor confirmation remains required for re-identification, population representation, COMPLETE rule, unknown handling, active/inactive transitions and revalidation.

• Claim 31/species-selective toxicant: architecture is supported; a concrete inventor-conceived toxicant species/class and selectivity basis remain required for broad early-priority reliance.

• Claim 41/reproductive control: representative GnRH/PZP/diazacon context exists; inventor confirmation of actually contemplated agent(s), route(s), and protocol remains required.

• Claim 51/genetic modification: broad reliance remains blocked until the inventors provide a concrete mechanism, biological effect, delivery route and enabling implementation or the branch is narrowed/deferred.

• Claim 111/broad target-animal genus: representative implementations are disclosed, but inventor confirmation and full-scope enablement analysis remain required for the widest genus.

3. Work that proceeds without waiting for inventor answers

• Formal element-by-element prior-art charting of all 14 independent families.

• USPTO Patent Public Search / Google Patents / citation-family search expansion and search-log capture.

• Functional-language / §112(f) audit of system/software claims against disclosed structure and algorithms.

• Claim dependency and redundancy analysis for the current 135-claim universe, without pruning the provisional-stage disclosure.

• Attorney-review issue list and filing-package organization.

4. MPEP control points

• Current MPEP §2163: textual presence alone does not establish adequate written description; genus support must convey possession through representative species or common identifying characteristics appropriate to the scope.

• Current MPEP §2164: enablement must reach the claimed scope without undue experimentation.

• Current MPEP §2173: functional limitations are not inherently improper but definiteness depends on context and the disclosure.

• Current MPEP §2181: generic placeholders coupled to function can invoke §112(f) if sufficient structure/acts are not recited or disclosed.

• Claims remain provisional-stage support/patentability probes, not a filing gate or ceiling.

5. Resume protocol

• When Robert sends 'Resume', continue from the highest-priority task that can be advanced without waiting for an unanswered inventor question.

• Current next executable task is PAT-042 formal prior-art claim charting. PAT-041 inventor responses remain a parallel dependency for confirmation-gated §112(a) branches.

• At each material checkpoint rebuild the fossil-free canonical archive with current files, manifest and SHA-256 hashes.